## Sheet1
TIMELINES FOR IMPLEMENTATION OF e-NHIA PENDING LOW HANGING DELIVERABLES.
Status Bar
S/n | Delivearable | Timeline | Start Date | End-Date | Responsibility | Remarks | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01
1 | Implementation of Signed MOU T&C | 90 days | 7th Sept 2023 | 30th Sept 2023 | NIGCOMSAT | Extension to be formalized by NHIA and NIGCOMSAT Legal Depts
2 | Handover of Website (NIGCOMSAT to write to Content Oasis to provide the account details of NHIA admin that will be responsible for record and security purpose) | 3 days | 7th Jun 2023 | 9th June 2023 | NIGCOMSAT | NHIA webmater to be given full Administrative Rights |  | N/A | N/A | N/A
3 | Handover of e-NHIA platform with Administrative Access Righths and priviledges (NIGCOMSAT to write to Content Oasis to provide the account details of NHIA admin that will be responsible for record and security purpose) | 8 days | 7th Jun 2023 | 14th Jun 2023 | NIGCOMSAT | Adminstrative access rights and documentation to HIBPA solutions, Enrolees database, GBB Data center, MCC, Recovery centres |  | N/A | N/A | N/A
4 | Full operationalization of NHIA Call Management center nationwide(This is for IT SKY) | 24 days | 7th Jun 2023 | 30th Jun 2023 | NHIA (Procurement Dept), NIGCOMSAT | Installation of SOPHOS security software in procurement proces to be concluded; NIGCOMSAT then activate Call center functionalities |  | N/A | N/A | N/A
5 | Integration of ID card printing with payment solution (No resourses available to implement this from Content to Inspired Mobile) | 10 days | 7th Jun 2023 | 17th Jun 2023 | NIGCOMSAT | Immediate integration of ID card solution with existing Payment module of HIBPA, while upgrade would later be considered |  | N/A | N/A | N/A
6 | Renewal of GIFSHIP (for all variants, Groups, Family, Individual) with changes in status. (1- NHIA to tell us what is remaining and give letter of award to that effect. 2.No resourses available to implement this from Content to Inspired Mobile) | 21 days | 7th Jun 2023 | 30th Jun 2023 | NIGCOMSAT | Business process already submitted to NIGCOMSAT |  | N/A | N/A | N/A
7 | Full automaion of NYSC solution. (NHIA to write to NIGCOMSAT telling them exactly all the features needed. Also, no enough resourses to proceed from Content) | 21 days | 9th Jun 2023 | 30th Jun 2023 | NIGCOMSAT | Meeting between NHIA (DICT and FSD) with NGICOMSAT to be held on Friday, 9th Jun |  | N/A | N/A | N/A
8 | Full automation of enrolees register generation with Adminsitrative rughts and priviledges, and habdo0ver to DICT (NHIA to write to NIGCOMSAT giving the accounts since FSD has taken over. But in the meeting, it was stated by samad that due to the attack at MCC, a register software be created online to allow states to cut register anywehre in the country | 21 days | 9th Jun 2023 | 30th Jun 2023 | NIGCOMSAT | Meeting between NHIA (DICT and FSD) with NGICOMSAT to be held on Friday, 9th Jun |  | N/A | N/A | N/A
9 | Real-time Data replication from e-NHIA Database at GBB to Monitring and Control Center (MCC), and Disaster Recovery centers) (Meeting to be held at NHIA to iron out the technical details) | 90 days | 8th Jun 2023 | 30th Sept 2023 | NIGCOMSAT | Technical design and modlaities To be further discussed between DICT NHIA and NIGCOMSAT